NASO

# Internal Project Cost Breakdown

Project Duration: Approximately 6–10 weeks

Confidential — For Internal Planning & Team Discussion

# 1. Project Pricing Summary

Proposed total project fee: ₦1,500,000

This internal estimate is intended to guide project planning and team discussions. The final client quotation should be issued only after the discovery meeting confirms the scope.

| Work Area | Scope | Amount | Share |
| --- | --- | --- | --- |
| Discovery, Planning & Project Management | Requirements clarification, project planning, scope definition, meetings, coordination, and milestone management. | ₦150,000 | 10% |
| UI/UX Design & Visual Direction | Website structure, user flows, responsive interface design, key page layouts, and design refinement. | ₦225,000 | 15% |
| Frontend Website Development | Responsive website pages, navigation, product browsing, search/filtering, product pages, and customer-facing experience. | ₦300,000 | 20% |
| E-Commerce & Order Functionality | Shopping cart, checkout flow, order handling, customer accounts, and payment integration setup. | ₦300,000 | 20% |
| Procurement & Product Sourcing Features | Request-a-product form, bulk/wholesale inquiry workflow, procurement request handling, and quote request experience. | ₦225,000 | 15% |
| Admin Management & Business Operations | Product and category management, order management, request review, status updates, and basic content management. | ₦150,000 | 10% |
| Testing, Deployment & Launch | Quality assurance, responsive testing, bug fixing, deployment, domain connection, launch configuration, and handover. | ₦90,000 | 6% |
| Post-Launch Support & Handover | Initial support period, basic admin guidance, and assistance with issues related to the delivered scope. | ₦60,000 | 4% |

TOTAL PROJECT FEE: ₦1,500,000

# 2. Recommended Payment Milestones

| Milestone | Percentage | Amount | Payment Point |
| --- | --- | --- | --- |
| Project Initiation | 40% | ₦600,000 | Before work begins; covers discovery, planning, and initial design. |
| Development Milestone | 30% | ₦450,000 | After design approval and at the agreed development milestone. |
| Pre-Launch | 20% | ₦300,000 | When the platform is substantially complete and enters final testing. |
| Final Launch & Handover | 10% | ₦150,000 | Before or upon final launch and handover. |

# 3. Cost Assumptions

The ₦1,500,000 estimate assumes a single-brand e-commerce and procurement platform, not a multi-vendor marketplace.

The estimate assumes standard product catalog, ordering, payment, customer request, procurement inquiry, and admin workflows.

The estimate assumes the client provides company content, product information, product images, branding assets, and required account credentials in a timely manner.

The estimate includes standard payment gateway integration but does not include payment gateway transaction charges.

The estimate assumes standard deployment and does not include the purchase of premium third-party services unless specifically agreed.

The estimate does not include advanced logistics tracking, live shipping rate calculations, automated customs systems, ERP integrations, mobile applications, or AI procurement automation.

Any feature added after scope approval should be assessed separately for cost and timeline impact.

# 4. Excluded / Separately Billed Costs

Domain registration and renewal fees.

Hosting or infrastructure fees.

Payment gateway transaction charges.

Premium plugins, software, APIs, or third-party subscriptions.

Email, SMS, WhatsApp API, or messaging charges.

Professional product photography or video production.

Professional copywriting or translation services.

Logistics provider fees and delivery charges.

Third-party software or business system integrations not included in the approved scope.

# 5. Internal Delivery Plan

Target delivery remains approximately 6–10 weeks, subject to timely client feedback, content delivery, access to required third-party accounts, and approval of each project milestone.

Week 1: Discovery, requirements confirmation, information architecture, and project setup.

Weeks 1–2: UI/UX design and client review.

Weeks 2–6: Core website and platform development.

Weeks 5–7: E-commerce, payment, procurement, sourcing, and admin functionality.

Weeks 7–8: Integration, testing, quality assurance, and revisions.

Weeks 8–10: Final deployment, launch preparation, handover, and post-launch support.

# 6. Commercial Strategy

The ₦1,500,000 figure should be treated as the team's internal baseline for the currently anticipated Version 1 scope. It should not be presented as a final fixed quotation until the discovery discussion confirms the client's exact requirements.

If the discovery process reveals additional complexity, the team should revise the scope and pricing before signing the final agreement. The strongest commercial approach is to maintain a clear distinction between the Version 1 launch scope and optional future enhancements.

# 7. Recommended Future Add-Ons

Advanced logistics tracking.

Multi-vendor marketplace functionality.

Multi-currency and multi-country support.

Automated shipping rate calculations.

Supplier management and supplier comparison.

Corporate procurement accounts.

Advanced reporting and analytics.

ERP or accounting integrations.

AI-assisted product sourcing.

Automated quotation and procurement workflows.

Mobile applications.